##### WBS 7.2.0.402 and VTO Analysis Program, Modeling Activities at NREL

General Information

| Program:* Auto-Filled in EERE SharePoint |  |
| --- | --- |
| Activity:* Auto-Filled in EERE SharePoint |  |
| Sub Activity:* Auto-Filled in EERE SharePoint |  |
| Project Title:* VTO Analysis Program, Modeling Activities at NREL |  |
| WBS: Auto-Filled in EERE SharePoint |  |
| Work Category:* AOP Project (Direct-Funded Lab Project) | EERE Crosscuts: Auto-Filled in EERE SharePoint |
| Current Year CPS Agreement #: Auto-Filled in EERE SharePoint | Prior Year CPS Agreement #: Auto-Filled in EERE SharePoint |
| Project Start: * 11/14/2022 | Planned End Date:* 12/31/2025 |
| FOA Number: | Project Duration |
| Overtarget Current Overtarget ☐ Approved, Previous Overtarget ☐ | Was this project merit reviewed (Y/N)? Y Fewer/Larger Project Exemption ☐ |
| Is this a grid integration project? ☐ | Merit reviewed year: FY23-24 |

| Project Ownership and Performers |  |
| --- | --- |
| EERE Project Lead Information | Lab Performer Information |
| Name: | Name: Paige Jadun |
| Email: | Email: paige.jadun@nrel.gov |
| Phone: | Phone: |

Detailed Project Information

Project Overview* This should be a complete and comprehensive description of the work in most cases several pages long. In terms of details think of it as the beginning of the scope of work. Tasks should be mentioned in this section, but the details of each task will be given below. The VTO Analysis Program plans, executes, and communicates technological, societal, economic, and interdisciplinary analyses for VTO, EERE, DOE, and external stakeholders. Programmatic efforts are designed to comprise an integrated strategy combining a strong foundation of data, relevant analytical models, and insightful applied analyses. The tasks included under this AOP project support the analytical modeling objectives of the Analysis Program.. Project Objectives* This field contains the project-specific goals, objectives, and expected outcomes. This space should be utilized to explicitly state what the outcomes and RESULTS of the project are – what we are trying to achieve – in most cases it should be at least a page long. Rapid emerging changes in the transportation and energy landscapes necessitate continuous development of tools to tackle new research questions as they arise. Correspondingly, activities under this AOP project will develop, improve, and apply vehicle technology-related analytical models, such as the Transportation Energy & Mobility Pathway Options (TEMPO) model. The efforts will include capability building and model enhancement, model upkeep, and responding to quick-turnaround strategic requests..

Project Management

Multi-Performer Projects

When two or more Labs are working in partnership with each other to achieve a common objective/goal, their AOP Projects are considered Multi-Performer Projects. The source for these projects typically come from Directly Funded AOPs. The Labs share the same AOP Project Title and overall objective. However, the Lab tasks are distinct from each other yet are interdependent. Thus, the performances of these Labs can affect each other (i.e. a delay in a Lab’s project can impact the others) and the overall goal.

Add Related Project

| Office: Choose an item. | Lab: Choose an item. |
| --- | --- |
| Activity: *Auto-Filled in EERE SharePoint | Sub Activity: *Auto-Filled in EERE SharePoint |
| Project Title (Can search for words found in title): Click here to enter text. |  |
| Office: Choose an item. | Lab: Choose an item. |
| Project Title (Can search for words found in title): Click here to enter text. |  |
| Office: Choose an item. | Lab: Choose an item. |
| Project Title (Can search for words found in title): Click here to enter text. |  |

Lead Lab Project? ☐

Project Plan

Milestones

EERE’s guidance is for each project to have one (1) Major Annual Milestone per year and Up to three (3) Progress Measures per year (envisioned to be quarterly during quarters where there is no Major Annual Milestone due). The Milestone is what you accomplished.  The Criteria is how we at HQ know you accomplished it.

| Milestone Name/Description* | Criteria* | End Date* | Type* |
| --- | --- | --- | --- |
| Annual publication of model enhancement(s) #2: Publication (draft paper) of at least one model enhancement and related results and insights for FY 2024 | Draft Paper | 12/31/2024 | Annual Milestone (Regular) |
| Quarterly check-in with DOE-VTO summarizing model and data updates and impact on results, summary of quick-turnaround analysis, prioritization of model enhancements, and the needs and timeline for publication of analysis insights and/or datasets (internally or publicly) | PowerPoint Presentation | 3/31/2025 | Quarterly Progress Measure (Regular) |
| Model enhancement on transportation affordability: Implementation and related analysis on at least one model enhancement focused on on improved representation of transportation costs and affordability. | PowerPoint Presentation | 6/30/2025 | Quarterly Progress Measure (Regular) |
| Used Vehicle Market: Slide deck summarizing implications of using regional LDV survival curves in TEMPO to represent the used vehicle market | PowerPoint Presentation | 06/30/2025 | Quarterly Progress Measure (Regular) |
| Summary of model upkeep activities, updates, and estimated impacts on results for FY 2025 | PowerPoint Presentation | 9/30/2025 | Quarterly Progress Measure (Regular) |

Go/No-Go Decisions

EERE’s guidance is for each project to have one (1) Go-No Go Milestone every 12-18 months.

Add Go/No-Go Decision –If a project is in its last year it most likely does not require a go/no-go. Do NOT create a go/no-go with a date that corresponds to the last day of the project please!

| Name* | Description* | Criteria* | Date* |
| --- | --- | --- | --- |
| Click here to enter text. | Click here to enter text. | Click here to enter text. | Enter a date. |
| Click here to enter text. | Click here to enter text. | Click here to enter text. | Enter a date. |

Risks and Mitigation (Optional)

The purpose of this page is to identify and document any risks that are associated with the AOP project.

Add New Risk

| Name* | Status | Classification (scope, cost, schedule, regulatory) | Target Completion Date | Severity* | Response Plan | Risk Response (accept, avoid, transfer, mitigate) | Risk Probability (low, med, high) | Description* |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Click here to enter text. | Choose an item. |  | Click here to enter a date. | Choose an item. | Choose an item. |  |  | Click here to enter text. |
| Click here to enter text. | Choose an item. |  | Click here to enter a date. | Choose an item. | Choose an item. |  |  | Click here to enter text. |
| Click here to enter text. | Choose an item. |  | Click here to enter a date. | Choose an item. | Choose an item. |  |  | Click here to enter text. |

Modality Summary

Provide the percentage amount for each TRL and modality level in the EERE Modality Matrix below. The percentage should equal 100%. This matrix refers to the 9 types of project funding profiles/modes for research technology readiness levels and other program funding profiles in taking projects from Basic Research to Market Deployment.

| Modality # | Modality(s) |  | Weight (%) | Total FY25 Cost Plan |
| --- | --- | --- | --- | --- |
| 1 | Early-Stage R&D (TRL 1-3) |  |  |  |
|  | TRL 1 | Basic principles observed and reported: Scientific problem or phenomenon identified. Essential characteristics and behaviors of systems and architectures are identified using mathematical formulations or algorithms. The observation of basic scientific principles or phenomena has been validated through peer-reviewed research. Technology is ready to transition from scientific research to applied research. | 0% |  |
|  | TRL 2 | Technology concept and/or application formulated: Applied research activity. Theory and scientific principles are focused on specific application areas to define the concept. Characteristics of the application are described. Analytical tools are developed for simulation or analysis of the application. | 30% | 177,000 |
|  | TRL 3 | Analytical and experimental critical function and/or characteristic proof of concept: Proof of concept validation has been achieved at this level. Experimental research and development is initiated with analytical and laboratory studies. System/integrated process requirements for the overall system application are well known. Demonstration of technical feasibility using immature prototype implementations are exercised with representative interface inputs to include electrical, mechanical, or controlling elements to validate predictions. | 50% | $295,000 |
| 2 | Mid-Stage RD&D (TRL 4-6) |  |  |  |
|  | TRL 4 | Component and/or process validation in laboratory environment- Alpha prototype (component): Standalone prototyping implementation and testing in laboratory environment demonstrates the concept. Integration and testing of component technology elements are sufficient to validate feasibility. | 20% | $118,000 |
|  | TRL 5 | Component and/or process validation in relevant environment- Beta prototype (component): Thorough prototype testing of the component/process in relevant environment to the end user is performed. Basic technology elements are integrated with reasonably realistic supporting elements based on available technologies. Prototyping implementations conform to the target environment and interfaces. | 0% |  |
|  | TRL 6 | System/process model or prototype demonstration in a relevant environment- Beta prototype (system): Prototyping implementations are partially integrated with existing systems. Engineering feasibility fully demonstrated in actual or high fidelity system applications in an environment relevant to the end user. | 0% |  |
| 3 | Late-Stage RD&D (TRL 7-8) |  |  |  |
|  | TRL 7 | System/process prototype demonstration in an operational environment- Integrated pilot (system): System prototyping demonstration in operational environment. System is at or near full scale (pilot or engineering scale) of the operational system, with most functions available for demonstration and test. The system, component, or process is integrated with collateral and ancillary systems in a near production quality prototype. | 0% |  |
|  | TRL 8 | Actual system/process completed and qualified through test and demonstration- Pre-commercial demonstration: End of system development. Full-scale system is fully integrated into operational environment with fully operational hardware and software systems. All functionality is tested in simulated and operational scenarios with demonstrated achievement of end-user specifications. Technology is ready to move from development to commercialization. | 0% |  |
| 4 | Testing, Data Collection and Data Dissemination |  | 0% |  |
| 5 | Strategic, Market and Techno-Economic Analysis |  | 0% |  |
| 6 | Removing Deployment Barriers |  | 0% |  |
| 7 | Technical Management |  | 0% |  |
| 8 | Major Subcontracting |  | 0% |  |
| 9 | Facility Costs |  | 0% |  |
| Project Total |  |  | 100% | $590,000 |

Project Impact

Project Impacts

The purpose of this section is to identify and document how this newly planned/created project will impact the target audiences. Please include more details here than you have in the past.

Deliverable/Product or "output" Description:* The activities under this AOP project see to develop, improve and apply vehicle technology-related analytical models. The efforts include vehicle sales dynamics with integrated stock modeling and emphasis placed on sophistication in use segmentation and heterogeneity, model analysis capability, model transparency and defensibility and effective/innovative results communication.

Audience/Customer: * DOE

Audience Use: (Outcome, or Impact, what is the intended use of "output" by Audience/Customer) * To inform and deepen knowledge

Communications/Outreach Strategy (to reach target audience): * Presentation draft publications and reports

Does this project involve significant industry engagement? ☐ (Significant industry engagement is defined as any direct contact, input, or collaboration with)

Description of Engagement: Click here to enter text.

Tasks and Subs Section

Tasks

The purpose of this page is to identify and document any tasks and subcontractors that are associated with the AOP project. There should be a greater level of detail provided than has been in the past. There should be at LEAST a page of description for each task. Think the same level of detail as a SOW. I find adding a page of text in the description box extremely hard to read.  For this template, please fill out the table except for the description and then below the table add each task and its description. Note: Planned Cost amounts provided in this AOP write up are initial estimates and final cost plans will be submitted into the EERE AOP SharePoint site.

Add a New Task

| Name* | Description | FY25 Planned Cost* | FY26 Planned Cost | FY27 Planned Cost |
| --- | --- | --- | --- | --- |
| Holistic Modeling of Future Transportation Energy Use | Implement TEMPO modeling enhancements and perform upkeep—including staff training, model maintenance, documentation, and data updates. Respond to VTO’s quick turnaround strategic requests and be available to run scenarios requiring alternative input assumptions, and produce key metrics, insights, and/or visualizations in a short timeframe. Additionally perform communication and project management, including engagement with the TEMPO steering committee and regular check-ins with DOE-VTO. Leads: Matteo Muratori and Paige Jadun Cross-project collaborations within VTO-Analysis: - Ensure alignment, consistency and leverage capabilities with “Managing Increased Electric Vehicle Shares on Bulk Power Systems” at NREL - Ensure alignment, consistency and leverage capabilities with “Assessing Opportunities for Travel Demand” at NREL - Ensure alignment, consistency and leverage capabilities with “Enhancing the EVI-X National Framework to Address Emerging Questions on Charging Infrastructure Deployment” at NREL - Coordinate with “Applied Vehicle Modeling and Simulation” at ANL to jointly develop scenarios of EV adoption and leverage TEMPO to estimate stock turnover, energy use, emissions, and other implications - Coordinate as applicable (per VTO directions) with “Energy, Emissions, and Environmental Modeling of Vehicle/Fuel Technologies with the GREET Life-Cycle Analysis Model” at ANL | $535,000 | $ 100,000 | $ Enter Cost |
| Used Vehicle Market | Process and analyze LDV vehicle registration data to develop regional survival statistics and analyses, in collaboration with Ruixiao Sun at ORNL and David Greene and Benjamin Leard at University of Tennessee – Knoxville. Test and implement regional LDV survival curves developed in this project to represent the used vehicle market and explore implications on overall stock modeling, subnational – national result consistency, and applicable analyses e.g. technology adoption implications across households enabled by these modeling upgrades. | $55,000 | $Enter Cost | $Enter Cost |

Task 1:  Holistic Modeling of Future Transportation Energy Use

Transportation is the largest source of energy use across end-use sectors in the United States and the second largest household expense. At the same time, the transportation system is rapidly changing, driven by advancements in vehicle and fuel technologies, new mobility options and business models, and evolving consumer preferences. Rigorous and comprehensive analysis tools are critical to understand the implications of potential future transistions. Modeling tools can be used to develop scenarios of technology adoption and simulate market dynamics for various communities to ultimately estimate energy use and emissions across the transportation sector as well as implications for the larger energy system.

This task will marshal the world-class resources and expertise of a multi-disciplinary team at the National Renewable Energy Laboratory (NREL) to maintain, update, and enhance NREL’s Transportation Energy & Mobility Pathway Options (TEMPO) model so that it may continue to provide valuable insights to VTO and other stakeholders through rapid answers to timely questions as they arise.

Specifically, this task includes maintaining and continuing development of NREL’s TEMPO model. The transportation and energy modeling landscapes are rapidly changing, requiring the continuous development of tools to tackle new research questions as they arise. To address these challenges, the objectives of this task are:

1. Capability building and model enhancements: The team will continue to innovate and enhance the TEMPO model through the refinement of existing elements, addition of new capabilities (e.g., include aspects not currently modeled endogenously in TEMPO), and by ensuring the model can answer relevant questions as they arise over the next three years. The enhancements will be informed by the TEMPO steering committee and prioritized by VTO to identify areas of more immediate relevance and ensure that the model is able address critical questions. This project will develop the modeling capabilities to quickly perform analysis on pressing topics of interest to DOE, further enabling TEMPO to be leveraged in future analysis efforts.

2. Model upkeep: The team will maintain a functional and up-to-date TEMPO modeling capability at NREL, train staff (including interns) to run the model and interpret model results, and update inputs to reflect the most recent trends and best available data.

3. Respond to quick-turnaround strategic requests: The team will respond to urgent analysis requests from VTO as they arise over time, such as quickly generating vehicle adoption scenarios to estimate sales, stock, energy use and emissions under differing assumptions, that can be answered with simple runs (TEMPO models national level scenarios in a few hours, and multiple scenarios can be run simultaneously utilizing NREL’s High Performance Computing [HPC] capabilities).

This support will further cement TEMPO’s positioning as a best-in-class transportation modeling tool, contribute to the modeling and analysis state-of-the-art, and allow DOE to answer critical questions on the future evolution of the transportation sector.

Task 2: Used Vehicle Market The ability to model used vehicle markets is becoming more and more important, especially to assess varying impacts of alternative technology adoption scenarios across consumers (e.g., estimate costs and benefits for different segments of the population). Funded by VTAP, ORNL is developing key modeling and analysis capabilities in this space, in collaboration with David Greene and Benjamin Leard at the University of Tennessee – Knoxville (UTK). NREL has data and resources to offer that the ORNL team has requested, particularly the vehicle registration data from Experian, and we are interested in supporting ORNL and in ensuring that we can implement the methodology in TEMPO.

Because the Experian LDV registration data is under license to NREL, the requested data must be processed and analyzed into a data product and approved for sharing. The work outlined here includes the planning, negotiation, and execution of that analysis. The core data product to be exchanged between NREL and ORNL/UTK will be LDV survival rates, by state, vehicle type, and powertrain type, for multiple pairs of years, including at least 2022-2023, 2021-2022, 2018-2019, and potentially data for other historical year pairs.

Additional analysis will include statistics related to survival by state (and county, where data resolution allows), vehicle type, and powertrain type, including age distributions and % stock as new sales (insights on turnover/longevity), and characterization of expected data features and anomalies of interest (e.g. deviations from average or national), such as the age, transfer, and survival of leased vehicles of age 2-4 years, and electric vehicles. Comparisons will be made to EIA's methodology on their version of regional survival statistics and how they are implementing them in the next NEMS/AEO. The NREL team will also implement the regional LDV survival curves developed in this project in TEMPO to represent the used vehicle market and explore implications.

Subcontractors

The purpose of this page is to identify and document any subcontractors that are associated with the AOP project. Note: Planned Cost amounts provided in this AOP write up are initial estimates and final cost plans will be submitted into the EERE AOP SharePoint site.

Add a Subcontractor

| Performer Org Name* | Responsibility | Sub Type* | Sub ID | Start Date* | End Date* | FY25 Planned Cost* | FY26 Planned Cost | FY27 Planned Cost |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Click here to enter text. | Click here to enter text. | Choose an item. |  | Choose a date | Choose a date | $Enter Cost | $Enter Cost | $Enter Cost |
| Click here to enter text. | Click here to enter text. | Choose an item. |  | Choose a date | Choose a date | $Enter Cost | $Enter Cost | $Enter Cost |
| Click here to enter text. | Click here to enter text. | Choose an item. |  | Choose a date | Choose a date | $Enter Cost | $Enter Cost | $Enter Cost |
| Click here to enter text. | Click here to enter text. | Choose an item. |  | Choose a date | Choose a date | $Enter Cost | $Enter Cost | $Enter Cost |

Place of Performance

Address different from lab? ☐

Address: 15013 Denver West Parkway

City: Golden

State: Colorado

Country: United States

Financial Section

Financials

The purpose of this page is to gather and calculate all the costs associated with the AOP Project. For projects with multiple labs, please submit financial tables for the project as a whole and for each lab individually, so I can make sure the numbers work out. Note: Planned Cost amounts provided in this AOP write up are initial estimates and final cost plans will be submitted into the EERE AOP SharePoint site.

Project Financial Details

| Funding Type |  | FY24 Projected Cost |  | FY 25 Beginning Uncosted |  | PY Unobligated Carryover |  | FY25 Budget Authority | FY25 Total Funding Level (Planned) | FY26 Beginning Uncosted (Planned) | FY26 Budget Authority (Planned) |  | FY27 Beginning Uncosted (Planned) |  | FY27 Budget Authority (Planned) |  | FY25 Allocation Method (manual or 12 month) |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| VT1800000-05450-10005702 |  | $550,000 |  | $190,000 |  |  | $500,000 | $690,000 | $100,000 |  |  |  |  |  |  |  |  |
| Operating |  | $550,000 |  | $190,000 |  | $ | $500,000 | $690,000 | $100,000 |  | $ |  | $ |  | $ |  | $ |
| Capital Equip |  | $ |  | $ |  | $ | $ | $ | $ |  | $ |  | $ |  | $ |  | $ |
| Totals (All) |  | $550,000 |  | $190,000 |  | $ | $500,000 | $690,000 | $100,000 |  | $ |  | $ |  | $ |  | $ |

Project Cost Plan

|  |  |  |  |  | FY25 |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Funding Type | OCT | NOV |  | DEC |  | JAN | FEB | MAR | APR | MAY | JUN | JUL | AUG | SEP | Total | FY26 Beginning Uncosted |
| VT1500000 | $49,160 | $49,160 |  | $49,160 |  | $49,160 | $49,160 | $49,160 | $49,160 | $49,160 | $49,160 | $49,160 | $49,160 | $49240 | $590,000 | $100,000 |
| Operating |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | $100,000 |
| Capital Equip | $ | $ |  | $ |  | $ | $ | $ | $ | $ | $ | $ | $ | $ | $ | $ |
| Totals (all) | $49,160 | $49,160 |  | $49,160 |  | $49,160 | $49,160 | $49,160 | $49,160 | $49,160 | $49,160 | $49,160 | $49,160 | $49240 | $590,000 | $100,000 |

| FY26 |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| Funding Type/B&R | Q1 Cost | Q2 Cost | Q3 Cost | Q4 Cost | Total |
| B&R Code #1 | 100,000 |  |  |  |  |
| Capital |  |  |  |  |  |
| Operating | 100,000 |  |  |  |  |
| Total | 100,000 |  |  |  |  |

| FY27 |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| Funding Type/B&R | Q1 Cost | Q2 Cost | Q3 Cost | Q4 Cost | Total |
| B&R Code #2 |  |  |  |  |  |
| Capital |  |  |  |  |  |
| Operating |  |  |  |  |  |
| Total |  |  |  |  |  |

Encumbered Balances Table

| Funding Type | Oct | Nov | Dec | Jan | Feb | March | April | May | June | July | August | Sept |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| VT1500000 |  |  |  |  |  |  |  |  |  |  |  |  |
| Operating |  |  |  |  |  |  |  |  |  |  |  |  |
| Capital Equipment |  |  |  |  |  |  |  |  |  |  |  |  |
| Totals |  |  |  |  |  |  |  |  |  |  |  |  |

Project Cost Breakdown

| Category | FY 2025 Planned Cost | FY 2026 Planned Cost | FY 2027 Planned Cost |
| --- | --- | --- | --- |
| In-House Labor | $575,000 | $100,000 | $ |
| Subcontracts | $ | $ | $ |
| Travel | $15,000 | $ | $ |
| Capital Equipment | $ | $ | $ |
| Supplies | $ | $ | $ |
| Other | $ | $ | $ |
| Total | $590,000 | $ | $ |

Travel Section

Travel

The purpose of this page is to gather and calculate all the travel expenses associated with the AOP Project. Note: Planned Cost amounts provided in this AOP write up are initial estimates and final cost plans will be submitted into the EERE AOP SharePoint site.

| Month | FY* | Travel Type |  |  |  | Destination* | Purpose | Estimated Cost* |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| ​​Jun​ | 2025​​ | ​​Domestic​ | ​​VTO Annual Merit Review​ | ​​Planning to send up to two people for 2025 VTO Annual Merit Review at $2,500/person​ |  | $​5,000​ |  |  |
| Jul | 2025​​ | ​​Domestic​ | NREL |  | Planning to send up to 4 remote team members to NREL for onsite planning, TEMPO strategy discussions, and discussion of model results and/or model enhancements at $2,500/person. |  |  | $10,000 |
| Enter Month | Enter FY | Choose an item. |  |  |  | Click here to enter text. | Click here to enter text. | $Enter Cost |
| Enter Month | Enter FY | Choose an item. |  |  |  | Click here to enter text. | Click here to enter text. | $Enter Cost |

Reports/Link Projects

Lab Reporting

| Reports No report required ☐ |  |
| --- | --- |
| Report Title | Report Frequency |
| Cost and Obligations Report | Quarterly (Q) |
| Progress Report | Quarterly (Q) |
| Annual Milestone Report | Yearly (Y) |
| Special Status Report | Choose an item. |
| Journal Article-Accepted Manuscript | Choose an item. |
| Scientific/Technical Conference Paper/Presentation/Proceeding | Choose an item. |
| Scientific/Technical Software & Manual | Choose an item. |
| Scientific/Technical Dataset | Choose an item. |
| Other ST (Dissertation/Thesis) | Choose an item. |
| Invention Certification | Choose an item. |
| Intellectual Property Reporting | Choose an item. |
| Include Other Report | Choose an item. |